## OS
WORKING GROUPS MONTHLY ACTIONS |  |  |  | SEPTEMBER
Part complete
WORKING GROUP: |  | OPEN SPACES |  | Complete
LEAD |  | L. Church, |  | Outstanding
RESPONSIBILITIES: To meet, monitor and report on the following:
Recreation Ground - Play and sports equipment, Concrete roundels,
Area behind Medway Inn, CCTV area |  |  | Naval Green - Maintenance of Furniture.
Wouldham Common - Fly Tipping, Litter Picking |  |  | Village Green - Maintenance of Furniture.
Grass Cutting - Ensure contract is adhered to. |  |  | Allotments - Liaise with Allotment Association
Develop and progress any special projects identified in the precept
To develop, support and monitor Risk Assessments in liaison with H&S
ISSUE RAISED | LEAD | ACTION TAKEN | ONGOING ACTIONS | NEXT STEPS/ COMPLETE/RESULT
Wetpour damage | JM | Repaired large holes under climbing frame | Need to complete repair under slide and fill in gaps around equipment | Need to look at complete resurface in next budget
Wetpour damage | JM | Purchased gap filler and green wetpour | Gap filler delivered. Wetpour needs to be re-ordered | Arrange a day to fill gaps around equipment
Trip risk due to security bolts next to container |  | Removed screws and placed in container | New bench arrived | Needs installing Purchase new chains and re-install security screws
Area by sub station in carpark | JM | Fully weeded and put bark down | Weeding continues | Need to add more plants
Fence by sub station | TY | Volunteer has re-used fence from the VH and installed to stop people walking over ground | Weed spray pathway | Completed. Ongoing maintenance
Roundals | ? |  | Needs weeding/pruning/repainting | May be start a guerillas gardening club?
New bin for Rec and relocate unused one onto path | TM | New bin installed, chased TMBC to relocate other one | TMBC initially didn't empty the bin. Met with the Waste Manager, should now be done weekly. | TMBC still progressing the relocation.
New rubbish bin being used as a dog bin | TM | Put a sign on it saying 'no dogs poo' directing to the actual dog poo bins at either end of the path. | Sign removed and dog poo bins not being used. | Write on bin
Meadow Way Pathway | TM | Strimmed path alongside school as emergency | Contractor cut by hand as difficult work around the rubbish. Flytipping reported to KCC | KCC have inspected and looking to provide licence for a skip to keep area clearer.
Rec Wall Survey | TM | Surveyor appointed to carry out a full structural condition survey of the wall | Report received, liaising with Trenport and solicitor re Covernants and any licence conditions | Seek legal advice on actions needed. Undertake immediate remedial works.
RESOLUTIONS TO FULL COUNCIL:
To approve remedial works to wall

## RFL
WORKING GROUPS MONTHLY ACTIONS |  |  |  | SEPTEMBER
Part complete
WORKING GROUP: |  | ROADS, FOOTPATHS & LIGHTING |  | Complete
LEAD |  | C.Collier Ward, |  | Outstanding
RESPONSIBILITIES: To meet, monitor and report on the following:
Notify relevant authorities/companies of potholes, damaged road furniture, fly tipping, and signage.
Monitor overgrown vegetation, safe pavement surfaces and report as necessary.
Report lights not working - electric equipment, any lights that have vegetation on them either causing safety issues or blocking out the light.
Village Car Park and pathway |  | monitor condition and signage
Special Projects: | develop and progress any special projects identified in the precept
ISSUE RAISED | LEAD | ACTION TAKEN | PROGRESS | NEXT STEPS COMPLETE/RESULT
Hedges and footpath alongside the allotments | JM | Hedges cut back 30/9 | Hedges and around Kissing Gate cut | Check and repair barb wire
Tramway Footpath | JM | Regularly cut bramble runners and saplings | Full hedge cut due October
Knowle Road speed restriction to 20mph | KCC | With KCC Design dept | Reported back to KCC | Keep chasing
Pilgrims Way surface repairs | KCC | Initial agreemement for KCC to resurface and repair passing bays | Filling of potholes complete | Need to keep pressure on to improve passing bays.
Hedges going along to Winchester House | KCC | KCC and Farmer liaising | KCC issued notice for work. | Undercut needed to stop new growth onto pathway.
Extra dark pathway on High Street caused by tree growth |  | Spoken to residents who suggest a low level solar light by placed on the wall to illuminate path | Discuss at PC Meeting | Discuss with KCC
Fly tipping on Hall Road footpath |  | Resident saw Schools contractor dump rubbish on KCC land | Resident reported to the School who instructed contractor to remove | Monitor
Footpath from Church to Rectory |  | Passed info to resident on land ownership | Carter Jonas (estate managers) have sent an inspector out to look at pathway. | ?
Footpath to Borstal |  | Inspected | Entrance due to be cut by GM Contractor
Increased traffic coming through No Entry | TY | Discussed again with County Council re having a temporary camera | Agreed with Police to do more sessions | Encourage Police to procecute
Hedge along Hall Road/Knowle Road/Pilgrims Way needs cutting back | TM | KCC issued notice to clear | Cut back 30/9
SUPPORT NEEDED:
RECOMMENDATIONS:
RESOLUTIONS TO FULL COUNCIL:

## VH
WORKING GROUPS MONTHLY ACTIONS |  |  |  | May
Part complete
WORKING GROUP: |  | VILLAGE HALL |  | Complete
LEAD |  | A. Marr, |  | Outstanding
DELEGATED RESPONSIBILITIES: To meet, monitor and report on the following:
To plan for the ongoing development with the VH Charity, making recommendations as appropriate
Oversee and agree the terms and conditions of use of the facilities
Oversee and agree the fees relating to the hire of the facilities
Ensure that regular risk assessments and health and safety checks are made in line with current legislation
Ensure the provision of safe and well-maintained facilities for the community use.
Ensure Governing/Deed of Trust document is adhered to
ISSUE RAISED | LEAD | ACTION TAKEN | PROGRESS/NEXT STEPS | COMPLETE/RESULT
Front garden | AMC | Group of volunteers sigened up and tidied up garden | Need to arrange regular days to maintain | Ongoing
Back garden | AMC/ TM | Needs clearing again | Need to look at large funding application to make the space more usable
Closure of VH Charity | AM / SB | Grant conditions have been sent to users | Funds have been sent. Those without bank accounts have been paid to PC to cover the cost of hall hire. | Final accounts to be submitted, then charity can be dissolved.
Bad debt | TM | Sent and received messages from user | Formal notice sent to start legal proceedings.
Terms and Conditions change | TM | Change conditions to include a £10 fine for leaving the vf | New conditions circulated to users and 'One-off' hirers for also changed.
P & L Certificate | TM | New Certificate of Insurance displayed
Showing films for YC and evenings for adults | TM | Purchased the required licence | Rocky Horror film for adults to be shown around Halloween, with bring your own drink and nibbles.
Transfer Freezer from container to Hall
SUPPORT NEEDED:
RECOMMENDATIONS:
RESOLUTIONS TO FULL COUNCIL: |  | To progress bad debt to Small Claims Court.
To approve new conditions for regular hirers

## H&S
WORKING GROUPS MONTHLY ACTIONS |  |  |  | SEPTEMBER
WORKING GROUP: |  | H & S
LEAD |  | J. MILES
RESPONSIBILITIES: To meet, monitor and report on the following:
Monitor the Councils compliance with relevant legislation and progress towards best practice in health and safety including 1974 Health & Safety at Work Act
To ensure the Council’s Health and Safety Policy is implemented, monitored, developed, communicated effectively, reviewed and amended as required.
To ensure suitable and sufficient funds, people, materials and equipment are provided to meet all health and safety requirements
Ensure adequate insurance cover is provided and renewed
Ensure any accidents, ill health and 'near miss’s are recorded, investigated and reported where necessary
Ensure any safety issues raised are thoroughly investigated and, when necessary, further effective controls implemented
Ensure contractors engaged are reputable, can demonstrate a good health and safety records and are made aware of relevant local health and safety rules and procedures
To develop an emergency plan/disaster recovery plan involving other partners/officials where necessary and assigning a designated competent person in charge of the planning and control measures for situations involving imminent danger
Develop flood risk planning in conjunction with (h)
Develop, monitor and review risk assessments linking with the relevant committee.
Ensure checks of capital equipment and assets are made and any remedial actions taken
ISSUE RAISED | LEAD | ACTION TAKEN | PROGRESS/NEXT STEPS | NEXT STEPS, COMPLETE/RESULT
Defibs | JM | Checked | No issues. PV had the wrong place on the map, so has been changed | Clerk to update Circuit
Lifebuoys | JM | Checked | No issues.
Loose legs on swings and seats too low | TM | Seats raised | Need to tighten top bolts now additional tool has arrived.
Connector loose on cargo net | TM | Sprayed with WD40, but bolt too seized to move | Arrange for specialist company to remove/replace.
Animal holes in Rec | TM/TY | Filled some | Fill remainder and monitor | Ongoing
Concrete base showing under gym equip | TM | Filled with sand | Need to consider a more permanate solution as it keeps getting kicked out. | Included in quote from repair company
Zip line vandalised | TM | Removed seat to stop anyone using it | New chain cover and D bolts purchased | Re-instate with new parts and put signage on posts re weight limit.
Gap filling around equipment | TM | Gaps filled around swings to test material | Small areas will need to be closed off to allow the wetpour to cure. | Continue to fill gaps.
ROSPA actions not able to be done by the PC | TM | ROSPA report sent to various contractors to quote for work | Only one company have said they can do the work, but are currently working on an installation. They will quote once free. | Agree quote once received
SUPPORT NEEDED:
RECOMMENDATIONS:
RESOLUTIONS TO FULL COUNCIL:

## Planning
WORKING GROUPS MONTHLY ACTIONS
WORKING GROUP: |  | PLANNING
LEAD
RESPONSIBILITIES: To meet, monitor and report on the following:
To make representations to the Local Planning Authority on applications for planning permission which have been notified to the Council
To make representations in respect of appeals against the refusal of planning permission
To identify and make representations to the relevant authorities in respect of enforcement action or any matters considered to be breaches of planning regulations;
The Working Group will consider each application on its merits.
All Parish Council members are notified of applications within 3 working days of Parish meeting and may be viewed via the Tonbridge and Malling Planning Portal. All Committee decisions will be recorded in the Parish Council minutes.
The Working Group, whilst considering the views of residents and other interested parties, is not duty bound to pass on these views when making its decision, they may submit a budget to the Council as part of the Council’s overall budget process.
ISSUE RAISED | LEAD | ACTION TAKEN | PROGRESS | RESULT/ COMMENT
Enforcement query raised for portacabin and parking on School Lane verge | TM | Reported to KCC and TMBC | Being investigated as not on the original planning permission
Enforcement query raised for apparent building work taking place on Pilgrims Way and potentially an unauthorised extention | TM | Reported to TMBC Planning | Being investigated - 2021 extention application withdrawn and doesn't appear to have been re-submitted.
25/01476/PA: IVY COTTAGE, 740, PILGRIMS WAY. | TM | Proposed barn conversion to a residential 1 x 2-bed dwelling and associated landscaping alterations | Presented at Oct meeting
25/01321/PA: POOH CORNER, 6, TRAFALGAR CLOSE | TM | Part retrospective to amend planning application TM/23/03056 (Demolition of existing side extension and construction of a two storey annex providing accommodation for elderly relative, maintaining access into the building. Internal lift in the place of the stairs, when stairs become an issue) to include a first floor balcony | Presented at Oct meeting

## F&A
WORKING GROUPS MONTHLY ACTIONS
WORKING GROUP: |  | FINANCE
LEAD
DELEGATED RESPONSIBILITIES: To meet, monitor and report on the following:
To consider the quarterly budget monitoring reports provided by the Clerk with any recommendations being put to the Council.
To consider the annual budget and the annual precept and take recommendations and comments to the full council.
All Council members will be provided with a list of payments for approval prior to each Council meeting. Any payment can be queried at the Council meetings. If necessary, a vote be taken to authorise payment with the Chairman of the Council Meeting having the casting vote when there are equal numbers of votes.
A member of the WG will sign off the bank statement from the previous month, at each Council meeting.
During each Council meeting, 2 bank signatories, will agree payments for the month.
To monitor staffing in line with the Terms of Reference
ISSUE RAISED | LEAD | ACTION TAKEN | PROGRESS | COMPLETE/RESULT
New Bank Account |  | AM completed identy check with bank | chased bank for login details.
Change Bank mandate | TM | Agreed that TY would be new signatory
Note AGAR External Audit |  | Discussed at Oct Meeting | Return advised no matters that cause concern | Issued on Website 19/9
As part of Assertion 10 of the AGAR an IT Policy needs to be written | TM | Initial research on what is needed. | Clerk attended training on 2/10
SUPPORT NEEDED:
RECOMMENDATIONS:
RESOLUTIONS TO FULL COUNCIL: