## OS
WORKING GROUPS MONTHLY ACTIONS |  |  |  | NOVEMBER
WORKING GROUP: |  | OPEN SPACES
LEAD |  | L. Church,
RESPONSIBILITIES: To meet, monitor and report on the following:
Recreation Ground - Play and sports equipment, Concrete roundels,
Area behind Medway Inn, CCTV area |  |  | Naval Green - Maintenance of Furniture.
Wouldham Common - Fly Tipping, Litter Picking |  |  | Village Green - Maintenance of Furniture.
Grass Cutting - Ensure contract is adhered to. |  |  | Allotments - Liaise with Allotment Association
Develop and progress any special projects identified in the precept
To develop, support and monitor Risk Assessments in liaison with H&S
ISSUE RAISED | LEAD | ACTION TAKEN | ONGOING ACTIONS | NEXT STEPS/ COMPLETE/RESULT
Wetpour damage | JM | Purchased gap filler and green wetpour | Gap filler delivered. Wetpour needs to be re-ordered | Arrange a day to fill gaps around equipment
Area by sub station in carpark | JM | Fully weeded and put bark down | Company has agreed to plant more plants/bark etc and maintain in exchange for placing a A3 sign there | Need to agree to offer
Roundals | ? |  | Bulbs have been donated by A Marr | Needs weeding/ pruning/repainting and planting
New bin for Rec and relocate unused one onto path | TM | New bin installed, chased TMBC to relocate other one | Arranged for GM to clear bin as TMBC don't seem to be taking it, but clearing others | Awaiting reply from TMBC on situation
New rubbish bin being used as a dog bin | TM | Put a sign on it saying 'no dogs poo' directing to the actual dog poo bins at either end of the path. | Put an article in the Parish Magazine to say that if it doesn't stop, the bin will be removed.
Rec Wall Survey | TM | Solicitor appointed to deal with issues | Action Plan written for approval. Paperwork sent to the Solicitor for action. | Obtain quotes for work
Wildlife Area | TM | Needs Winter cut | Arranged for GM to complete by 6/12 | Need to look at ensuring cut back to the wall
Common overgrown | TM | Contractor has started to clear saplings | Contractor will go again and let us know when we can get to the blocks for removal

## RFL
WORKING GROUPS MONTHLY ACTIONS |  |  |  | NOVEMBER
WORKING GROUP: |  | ROADS, FOOTPATHS & LIGHTING
LEAD |  | C.Collier Ward,
RESPONSIBILITIES: To meet, monitor and report on the following:
Notify relevant authorities/companies of potholes, damaged road furniture, fly tipping, and signage.
Monitor overgrown vegetation, safe pavement surfaces and report as necessary.
Report lights not working - electric equipment, any lights that have vegetation on them either causing safety issues or blocking out the light.
Village Car Park and pathway |  | monitor condition and signage
Special Projects: | develop and progress any special projects identified in the precept
ISSUE RAISED | LEAD | ACTION TAKEN | PROGRESS | NEXT STEPS COMPLETE/RESULT
Tramway Footpath | JM | Regularly cut bramble runners and saplings | Full hedge cut due October | Completion due by 6/12
Knowle Road speed restriction to 20mph | KCC | With KCC Design dept | Reported back to KCC | Design currently being done by KCC to reduce speed limit to 20mph along the whole length
Hedges going along to Winchester House | KCC | KCC and Farmer liaising | Hedges cut, but debris is reducing width of path | Reported to KCC to instigate an undercut
Extra dark pathway on High Street caused by tree growth |  | Spoken to residents who suggest a low level solar light by placed on the wall to illuminate path | Report made to KCC to pollard/crown reduce trees which are under TPO's | KCC have inspected and report no works are currently needed.
Footpath to Borstal |  | Inspected | Entrance due to be cut by GM Contractor
Winter Salt/bins | TM | Unusable bins at the top of Knowle Road and School Lane | Reported to KCC to remedy
Hedge along Hall Road/Knowle Road/Pilgrims Way needs cutting back | TM | KCC issued notice to clear | Cut back 30/9 | KCC side of Hall Road now needs cutting back.

## VH
WORKING GROUPS MONTHLY ACTIONS |  |  |  | NOVEMBER
WORKING GROUP: |  | VILLAGE HALL
LEAD |  | A. Marr,
DELEGATED RESPONSIBILITIES: To meet, monitor and report on the following:
To plan for the ongoing development with the VH Charity, making recommendations as appropriate
Oversee and agree the terms and conditions of use of the facilities
Oversee and agree the fees relating to the hire of the facilities
Ensure that regular risk assessments and health and safety checks are made in line with current legislation
Ensure the provision of safe and well-maintained facilities for the community use.
Ensure Governing/Deed of Trust document is adhered to
ISSUE RAISED | LEAD | ACTION TAKEN | PROGRESS/NEXT STEPS | COMPLETE/RESULT
Front garden | AMC | Creation of paved area and suitable ramp agreed to be included in precept | LC to obtain quotes and design
Back garden | AMC/ TM | Needs clearing again | Need to look at large funding application to make the space more usable | Forward planning allocating precept funds to reserves
Closure of VH Charity | AM / SB | Final accounts submitted and formal request to close the charity has been sent | Charity Commission have confirmed closure with no issues | Complete
Bad debt | TM | Sent and received messages from user | Formal notice sent to start legal proceedings. Followed up by hard copy posted to his address
Showing films for YC and evenings for adults | AMC | Next film needs to be agreed | Look at a Christmas family film
Trip risk on steps into back room | NT | Found hand rail that can be attached to the doorway as an aid. | Install hand rail
Transfer Freezer from container to Hall | JM | Now space is available in Hall, transfer freezer

## H&S
WORKING GROUPS MONTHLY ACTIONS |  |  |  | NOVEMBER
WORKING GROUP: |  | H & S
LEAD |  | J. MILES
RESPONSIBILITIES: To meet, monitor and report on the following:
Monitor the Councils compliance with relevant legislation and progress towards best practice in health and safety including 1974 Health & Safety at Work Act
To ensure the Council’s Health and Safety Policy is implemented, monitored, developed, communicated effectively, reviewed and amended as required.
To ensure suitable and sufficient funds, people, materials and equipment are provided to meet all health and safety requirements
Ensure adequate insurance cover is provided and renewed
Ensure any accidents, ill health and 'near miss’s are recorded, investigated and reported where necessary
Ensure any safety issues raised are thoroughly investigated and, when necessary, further effective controls implemented
Ensure contractors engaged are reputable, can demonstrate a good health and safety records and are made aware of relevant local health and safety rules and procedures
To develop an emergency plan/disaster recovery plan involving other partners/officials where necessary and assigning a designated competent person in charge of the planning and control measures for situations involving imminent danger
Develop flood risk planning in conjunction with (h)
Develop, monitor and review risk assessments linking with the relevant committee.
Ensure checks of capital equipment and assets are made and any remedial actions taken
ISSUE RAISED | LEAD | ACTION TAKEN | PROGRESS/NEXT STEPS | NEXT STEPS, COMPLETE/RESULT
Defibs | JM | Checked | No issues. | Clerk to update Circuit
Lifebuoys | JM | Checked, spoke to Trenport inspector about resetting | No issues. Lifebuoys are now staying set, with no 'tamper' indications.
Loose legs on swings and seats too low | TM | Seats raised | Need to tighten top bolts now additional tool has arrived.
Connector loose on cargo net | TM | Sprayed with WD40, but bolt too seized to move | Item ordered for installation by Playsource.
Dips and wear around 5-a-side goals | TM | Rospa suggested removing posts | New posts have been ordered from Playsource to be installed in alternative position | Fill worn areas
Animal holes in Rec | TM/TY | Filled some | Fill remainder and monitor | Ongoing
Concrete base showing under gym equip | TM | Filled with sand | Need to consider a more permanate solution as it keeps getting kicked out. | Discuss solutions with Playsource when on site.
Football training | TM | Permission given for group to use the Rec with floodlights | Ins and Risk Assessment received | Coach will ensure holes are filled before each session.
Gap filling around equipment | TM | Gaps filled around swings to test material | Small areas will need to be closed off to allow the wetpour to cure. | Continue to fill gaps.
Dog Treat Van | TM | Public Liability Cert received | Confirmed registered business. Spoken to TMBC about any other licences needed to support new business | Open Day event planned for 7th December
DBS Checks | TM/ AMC | Some volunteers still need to do checks | AMC to give each volunteer a copy of the Safeguarding Policy